## Template
Decision Matrix
Project Name
Document ID
Document Type
Status
Last Update
Target Release
Confidentiality
Created date
Target Release
Author
Aprovers
Stakeholders
Supersedes / replaces
Linked epic/ticket
Parent OKR / strategic initiativ
Regulatory refs
|  | Values |  |  |  |  | Normalized Values |  |  |  | Final Scores |  |  | Notes
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C | Weight | Option A | Option B | Option C
list criteria here | [10 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
[11 empty] | #VALUE! | #VALUE! | #VALUE!
Score Totals | [6 empty] | 0 | 0 | 0 |  | #VALUE! | #VALUE! | #VALUE!
Add your scale measure definitions here.
Scale Measure for [add criteria name here]
| Score | Scale Condition
5
4
3
2
1

## Sample
Sample Decision Matrix Construction
Example: Laptop Selection
Steps 0 - 2
First, always see what's already been done.
Then begin creating your decision matrix.
Values
Criteria |  | Option A | Option B | Option C
Battery Life
Cost
Weight
CPU
Memory
Warranty Coverage
Graphics
Future Availability
Score Totals
Graphics Performance Measurement Scale
| Score | Scale Condition
| 5 | Maximum resolution is obtained at highest frame rate for all sample programs
| 4 | Maximum resolution is obtained at highest frame rate for 3 out of 5 sample programs, Remaining 2 can be run at the 2nd largest resolution at the highest frame rate
| 3 | Maximum resolution is obtained at highest frame rate for 1 out of 5 sample programs, Remaining 4 can be run at the 2nd largest resolution at the 2nd highest frame rate
| 2 | 2nd highest resolution is obtained at 2nd highest frame rate for 3 out of 5 sample programs, Remaining 2 can be run at the 2nd largest resolution at the 3rd highest frame rate
| 1 | All sample programs, can be run at the either the 2nd largest resolution at the 3rd highest frame rate, or the 3rd largest resolution and the 2nd largest resolution
Steps 3 - 4
Values
Criteria |  | Option A | Option B | Option C | Min Value | Max Value
Battery Runtime |  | 15 hrs | 600 min. | 12 hrs | 8 hrs
Cost (dollars) |  | 850 | 500 | $50/month |  | 1000
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7
CPU |  | 2.0 GHz | 1.0 GHz | 1.7 GHz |  | 1.0 GHz
Memory |  | 2 GB | 1.75 GB | 1280 MB | 1 GB
Warranty Coverage |  | 100% | 80% | 99%
Graphics |  | 5 | 3 | 4 |  |  | It is rare to have a min or max value for a rating system you have come up with,
Future Availability |  | 5 yrs | yes | N/A | yes |  | unless the rating system being used was originally developed for something else or is a more generic rating system.
Score Totals
Step 5
|  | Values |  |  |  |  | Normalized Values
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C
Battery Runtime |  | 15 hrs | 600 min. | 12 hrs | 8 hrs
Cost |  | 850 | 500 | $50/month |  | 1000
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7
CPU |  | 2.0 GHz | 1.0 GHz | 1.7 GHz |  | 1.0 GHz
Memory |  | 2 GB | 1.75 GB | 1280 MB | 1 GB
Warranty Coverage |  | 100% | 80% | 99%
Graphics |  | 5 | 3 | 4
Future Availability |  | 5 yrs | yes | N/A | yes
Score Totals
Normalization Methods
Method 1: Take the largest value and divide all values by that
|  | Option A | Option B | Option C
Battery Runtime |  | 15 hrs | 600 min. | 12 hrs
|  | 15 | 10 | 12 | Convert Units
[6 empty] | Largest Option value = |  | 15
Normalized scores |  | 1 | 0.66667 | 0.8 | Divide by Largest Value
Method 2: If smaller is better do the same as in Method 1 but then subtract your answer from 1
|  | Option A | Option B | Option C
Cost |  | 850 | 500 | $50/month
|  | 850 | 500 | 600 | Convert values based on assumption of 1 year of use
[6 empty] | Largest Option value = |  | 850
|  | 1 | 0.58824 | 0.70588 | Divide by Largest Option value
Normalized scores |  | 0 | 0.41176 | 0.29412 | In this example, lower cost is better, so subtract each option score from 1
Method 3: Compare to a baseline value
|  | Option A | Option B | Option C
Weight (pounds) |  | 5 | 3.5 | 2
[6 empty] | Set a Base Line weight = |  | 3
|  | 2 | 0.5 | -1 | Calculate differences from the base line for each option
Determine the allowable range of variation from the baseline based on stakeholder needs (here we'll use a maximum absolute difference = 2)
[6 empty] | Range size is twice the maximum absolute difference, so the range size = | [5 empty] | 4
|  | 0.5 | 0.125 | -0.25 | Divide by the range size
|  | 1 | 0.625 | 0.25 | Add 0.5 to shift the scale (was a -0.5 to 0.5 scale , now it is a 0 to 1 scale)
Normalized scores |  | 0 | 0.375 | 0.75 | In this example, lower weight is better, so then subtract each option score from 1
Method 4: Come up with a ranking system like what was done to measure Graphics Performance
|  | Option A | Option B | Option C
CPU |  | 2.0 GHz | 1.0 GHz | 1.7 GHz
[6 empty] | Normalized Score Levels | Scale Conditions
[6 empty] | 1 | Has a processors speed at or above 1.8 GHz
[6 empty] | 0.75 | Has a processors speed at or above 1.5 GHz
[6 empty] | 0.5 | Has a processors speed at or above 1.3 GHz
[6 empty] | 0.25 | Has a processors speed at or above 1.0 GHz
[6 empty] | 0 | Has a processors speed at or above 0.75 GHz
Normalized scores |  | 1 | 0.25 | 0.75
Method 5: Sum all the values in a row and then divide all individual values by that sum
|  | Option A | Option B | Option C
Memory |  | 2 GB | 1.75 GB | 1280 MB
|  | 2 | 1.75 | 1.28 | Covert Units
[6 empty] | Sum of the values = |  | 5.03
Normalized scores |  | 0.39761 | 0.34791 | 0.25447 | Divide all values by the sum
|  | Values |  |  |  |  | Normalized Values
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C
Battery Runtime (hours) |  | 15 | 10 | 12 | 8 |  | 1 | 0.66667 | 0.8 | Method 1: Take the largest value and divide all values by that
Cost (dollars,1 yr duty) |  | 850 | 500 | 600 |  | 1000 | 0 | 0.41176 | 0.29412 | Method 2: If smaller is better do the same as in method 1 but then subtract your answer from 1
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7 | 0 | 0.375 | 0.75 | Method 3: Compare to a baseline value
CPU (GHz) |  | 2 | 1 | 1.7 |  | 1 | 1 | 0.25 | 0.75 | Method 4: Come up with a ranking system
Memory (GB) |  | 2 | 1.75 | 1.28 | 1 |  | 0.39761 | 0.34791 | 0.25447 | Method 5: Sum all the values in a row and then divide all individual values by that sum
Warranty Coverage (%) |  | 100 | 80 | 99 |  |  | 1 | 0.8 | 0.99 | Percentages are often simply converted to 0-1
Graphics (5 is best) |  | 5 | 3 | 4 |  |  | 1 | 0.6 | 0.8 | Rating Systems are often directly converted to a 0-1 scale
Future Availability (yrs) |  | 5 | yes | N/A | yes |  | 1 | 1 | 0.5 | For unknown values, it is common to give typically the worst or the median of all possible values. The median value for a 0 to 1 scale is given here for the unknown value.
Score Totals | [6 empty] | 5.3976 | 4.4513 | 5.1386
Step 6
|  | Values |  |  |  |  | Normalized Values
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C | Weight
Battery Runtime (hours) |  | 15 | 10 | 12 | 8 |  | 1 | 0.66667 | 0.8
Cost (dollars,1 yr duty) |  | 850 | 500 | 600 |  | 1000 | 0 | 0.41176 | 0.29412
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7 | 0 | 0.375 | 0.75
CPU (GHz) |  | 2 | 1 | 1.7 |  | 1 | 1 | 0.25 | 0.75
Memory (GB) |  | 2 | 1.75 | 1.28 | 1 |  | 0.39761 | 0.34791 | 0.25447
Warranty Coverage (%) |  | 100 | 80 | 99 |  |  | 1 | 0.8 | 0.99
Graphics (5 is best) |  | 5 | 3 | 4 |  |  | 1 | 0.6 | 0.8
Future Availability (yrs) |  | 5 | yes | N/A | yes |  | 1 | 1 | 0.5
Score Totals | [6 empty] | 5.3976 | 4.4513 | 5.1386
Weighting Examples
Give a Score Multiplier for Each Criterion Along a the Same Scale (maybe 0-1, or 1-5, or 1-3, or 1-10), All Criteria & Options Treated Independently
Weight
Battery Life |  | 5
Cost |  | 5
Weight |  | 3
CPU |  | 3
Memory |  | 5
Warranty Coverage |  | 3
Graphics |  | 4
Future Availability |  | 3
Give a Score Multiplier for Each Criterion such that the Weight Column Sums to 1
Weight
Battery Life |  | 0.16129
Cost |  | 0.16129
Weight |  | 0.096774
CPU |  | 0.096774
Memory |  | 0.16129
Warranty Coverage |  | 0.096774
Graphics |  | 0.12903
Future Availability |  | 0.096774
|  | 1 | Sum to check for 100%
|  | Values |  |  |  |  | Normalized Values
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C | Weight
Battery Runtime (hours) |  | 15 | 10 | 12 | 8 |  | 1 | 0.66667 | 0.8 | 0.16129
Cost (dollars,1 yr duty) |  | 850 | 500 | 600 |  | 1000 | 0 | 0.41176 | 0.29412 | 0.16129
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7 | 0 | 0.375 | 0.75 | 0.096774
CPU (GHz) |  | 2 | 1 | 1.7 |  | 1 | 1 | 0.25 | 0.75 | 0.096774
Memory (GB) |  | 2 | 1.75 | 1.28 | 1 |  | 0.39761 | 0.34791 | 0.25447 | 0.16129
Warranty Coverage (%) |  | 100 | 80 | 99 |  |  | 1 | 0.8 | 0.99 | 0.096774
Graphics (5 is best) |  | 5 | 3 | 4 |  |  | 1 | 0.6 | 0.8 | 0.12903
Future Availability (yrs) |  | 5 | yes | N/A | yes |  | 1 | 1 | 0.5 | 0.096774
Score Totals | [6 empty] | 5.3976 | 4.4513 | 5.1386
Step 7
Final Score = Sum(Rating * Weight) or Sum(Normalized Value * Weight)
Reject any Options that violate the min value, max value, or min rating thresholds
|  | Values |  |  |  |  | Normalized Values |  |  |  | Final Scores |  |  | Notes
Criteria |  | Option A | Option B | Option C | Min Value | Max Value | Option A | Option B | Option C | Weight | Option A | Option B | Option C
Battery Runtime (hours) |  | 15 | 10 | 12 | 8 |  | 1 | 0.66667 | 0.8 | 0.16129 | 0.16129 | 0.10753 | 0.12903
Cost (dollars,1 yr duty) |  | 850 | 500 | 600 |  | 1000 | 0 | 0.41176 | 0.29412 | 0.16129 | 0 | 0.066414 | 0.047438
Weight (pounds) |  | 5 | 3.5 | 2 |  | 7 | 0 | 0.375 | 0.75 | 0.096774 | 0 | 0.03629 | 0.072581
CPU (GHz) |  | 2 | 1 | 1.7 |  | 1 | 1 | 0.25 | 0.75 | 0.096774 | 0.096774 | 0.024194 | 0.072581
Memory (GB) |  | 2 | 1.75 | 1.28 | 1 |  | 0.39761 | 0.34791 | 0.25447 | 0.16129 | 0.064131 | 0.056115 | 0.041044
Warranty Coverage (%) |  | 100 | 80 | 99 |  |  | 1 | 0.8 | 0.99 | 0.096774 | 0.096774 | 0.077419 | 0.095806
Graphics (5 is best) |  | 5 | 3 | 4 |  |  | 1 | 0.6 | 0.8 | 0.12903 | 0.12903 | 0.077419 | 0.10323
Future Availability (yrs) |  | 5 | yes | N/A | yes |  | 1 | 1 | 0.5 | 0.096774 | 0.096774 | 0.096774 | 0.048387
Score Totals | [6 empty] | 5.3976 | 4.4513 | 5.1386 |  | 0.64478 | 0.54215 | 0.6101
Step 8
Comparing Final Score Results
Consider only those within x% (commonly 10%) of the top score | [6 empty] | Values
Top Score |  |  |  | 0.64478 |  |  | Option A | Option C | Option B
10% of Top Score |  |  |  | 0.064478 |  | Final Scores | 0.64478 | 0.6101 | 0.54215
Consider Options with Scores of this or higher |  |  |  | 0.5803 |  | highest to lowest
Graph
Plot the results by Final Score and look for a kinkor drop-off in the scores.