## Instructions
Interface Matrix — Basic Sample (Robot)
v1.0 ¦ 2012-08-01
Instructions:
This workbook contains one tab per subsystem. Each row records an interface specification owned by that subsystem. `Provided To` columns (left side) mark which other subsystems consume that spec. The Value and Units columns are kept separate to prevent unit-conversion errors. Group headers (column Q) collect related sub-specs (column R). The Row # column auto-increments via Excel formulas. See `08 - Creating the Interface Matrix.md` and `09 - Adding Values and Units.md`.

## Chassis Design
Interface Matrix Excerpt : Chassis Design Sheet
Chassis Design | Motor Drive | Power | Value | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Chassis Design
| Provided To | Provided To | 144 | in3 | X | 2012-06-25 | Jin | Nero | 2012-07-15 | 2012-08-01 | 5 | Total Volume Max
| Provided To |  | 10 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 |  |  | Total Volume Allocated to Motors
|  | Provided To | 12 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 |  |  | Total Volume Allocated to Power subsystem
| Provided To | Provided To | 2.5 | kg | X | 2012-06-28 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  | TotalComponent Weight Max
| Provided To |  | 2 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  |  | Total Weight Allocated to Motors
|  | Provided To | 0.5 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  |  | Total Weight Allocated to Power subsystem
|  |  | 1500 | $ |  | 2012-06-15 | Xing | Lesslie | 2012-06-15 | 2012-07-15 |  | Total Cost Allowed
|  |  | 150 | $ |  | 2012-07-13 | Xing | Lesslie |  | 2012-07-15 |  |  | Chassis Design Cost