## Instructions
Interface Matrix — Basic Sample (Robot)
v1.0 ¦ 2012-08-01
Instructions:
This workbook contains one tab per subsystem. Each row records an interface specification owned by that subsystem. `Provided To` columns (left side) mark which other subsystems consume that spec. The Value and Units columns are kept separate to prevent unit-conversion errors. Group headers (column Q) collect related sub-specs (column R). The Row # column auto-increments via Excel formulas. See `08 - Creating the Interface Matrix.md` and `09 - Adding Values and Units.md`.

## Chassis Design
Interface Matrix Excerpt : Chassis Design Sheet
Chassis Design | Motor Drive | Power | Value | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Chassis Design
| Provided To | Provided To | 144 | in3 | X | 2012-06-25 | Jin | Nero | 2012-07-15 | 2012-08-01 | 5 | Total Volume Max
| Provided To |  | 10 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 |  |  | Total Volume Allocated to Motors
|  | Provided To | 12 | in3 | X | 2012-06-26 | Jin | Nero | 2012-07-15 | 2012-08-01 |  |  | Total Volume Allocated to Power subsystem
| Provided To | Provided To | 2.5 | kg | X | 2012-06-28 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  | TotalComponent Weight Max
| Provided To |  | 2 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  |  | Total Weight Allocated to Motors
|  | Provided To | 0.5 | kg | X | 2012-06-29 | Hilary | Octavier | 2012-07-15 | 2012-08-01 |  |  | Total Weight Allocated to Power subsystem
|  |  | 1500 | $ |  | 2012-06-15 | Xing | Lesslie | 2012-06-15 | 2012-07-15 |  | Total Cost Allowed
|  |  | 150 | $ |  | 2012-07-13 | Xing | Lesslie |  | 2012-07-15 |  |  | Chassis Design Cost

## Motor Drive
Interface Matrix Excerpt : Motor Drive Sheet
Chassis Design | Motor Drive | Power | Value | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Motor Drive
[11 empty] | 5 | Power Information
|  | Provided To | 24 | V |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 |  |  | Motor Voltage
|  | Provided To | 1.7 | A |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 |  |  | Motor Current
|  | Provided To | 30 | W |  | 2012-07-11 | Yashoda | Jose |  | 2012-07-12 |  |  | Motor power rating
|  | Provided To | 24 | min. | X | 2012-06-28 | Allison | Yulia | 2012-06-30 | 2012-07-15 |  | Maximum Duration Usage
Provided To |  |  | 216 | $ |  | 2012-07-19 | Kelsey | Marc | 2012-07-05 | 2012-07-18 |  | Motor Cost
Motor Dimensions
Provided To |  |  | 62.5 | mm |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 |  |  | Motor Length
Provided To |  |  | 50 | mm |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 |  |  | Motor Dia.
Motor Weight
Provided To |  |  | 521 | g |  | 2012-07-11 | Horitz | Nick | 2012-07-05 | 2012-07-11 |  |  | Motors Weight
Provided To |  |  |  | kg |  | 2012-07-11 | Horitz | Nick |  | 2012-07-11 |  |  | Actual Weight used by Motor drive subsystem
Provided To |  |  | MotorGuide (Sec 1.2) | .docx |  | 2012-07-29 | Justin | Justine |  | 2012-08-15 |  | Motor Installation Guide

## Power
Interface Matrix Excerpt : Power Sheet
Chassis Design | Motor Drive | Power | Value | Units | Estimate? | Last Updated | Last Updated By | Interface Champ. | Est. Update Due Date | Actual Due Date | Row # | Power
| Provided To |  | 5, 12, 24 | V |  | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 | 5 | Voltages Supplied
| Provided To |  | less than 6 | A | X | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 |  | Max Current Draw
| Provided To |  | 24 | V |  | 2012-07-12 | Archie | Fritz | 2012-07-01 | 2012-07-12 |  | Max Voltage Supplied
Provided To |  |  | incl. components & shipping: 230 | $ |  | 2012-07-22 | Susan | Heidi | 2012-07-15 | 2012-07-20 |  | Power Board Cost
Provided To |  |  | PowerBoardInstructions (Sec 2.1) | .docx |  | 2012-07-22 | Rebecca | Ahmed |  | 2012-08-15 |  | Power Board Connection Instructions
Provided To |  |  | 12 x 2.5 x 1 | in. |  | 2012-07-16 | Susan | Heidi |  | 2012-08-15 |  | Power Board Dimensions
Provided To |  |  | 12.5 | in3 |  | 2012-07-20 | Susan | Heidi |  | 2012-07-20 |  | Actual Volume used by Power subsystem
Provided To |  |  | 0.21 | kg | X | 2012-07-20 | Susan | Heidi |  | 2012-07-20 |  | Actual Weight used by Power subsystem