## FMEA Master
FAILURE MODE ID | SUBSYSTEM | FAILURE MODE | FAILURE EFFECTS | POSSIBLE CAUSE | MMMME | INTERFACE REF | SEVERITY | LIKELIHOOD | RPN | RISK CRITICALITY | CORRECTIVE ACTION | ADJUSTED SEVERITY | ADJUSTED LIKELIHOOD | ADJUSTED RPN | ADJUSTED CRITICALITY | CORRECTIVE ACTION EFFORT | DETECTABILITY | TROUBLESHOOTING
FM.01 | surviving from FM.01 ¦ forms: FR.02(primary); FR.10(audit-cross-cut) | Spec generation hallucinates citations unsupported by DOCUMENTATION SOURCES | Founder approves spec with unsourced claims — EC10 citation-floor violation | Claude Sonnet 4.5 (DN.01-A) drifts; pgvector retrieval miss followed by LLM completion without grounded-retrieval gate enforcement | Method |  | 4 | 2 | 8 | MEDIUM | [form:FR.02] Grounded-retrieval gate enforces NFR.01 citation floor (per form_function_map FR.02 description); [nfr:NFR.01] Citation-floor NFR; primary mitigation per fmea_early FM.01.M1; [audit_cross_cut:CC.R02] Audit Event Store FR.10 records spec-emit events for after-the-fact citation review | 4 | 2 | 8 | MEDIUM | committed | 3 | Detectability remains imperfect — silent hallucinations within retrieved corpus still possible until SR-CORNELL validator agent ships.
FM.02 | surviving from FM.02 ¦ forms: FR.04(primary) | Approval fires without compliance policy check | Non-compliant spec passes review — potential SOC2/HIPAA/GDPR breach | DE.14 Compliance Policy not loaded when Review Gate Service (FR.04) evaluates OR.1 | Method |  | 4 | 1 | 4 | MEDIUM LOW | [form:FR.04] Review Gate Service enforces compliance-policy digest check (NFR.02); [nfr:NFR.02] Compliance-policy digest invariant; [audit_cross_cut:CC.R02] Audit policy version at every review event | 4 | 1 | 4 | MEDIUM LOW | committed | 3
FM.03 | surviving from FM.03 ¦ forms: FR.04(primary); FR.05(secondary) | Approved spec handoff corrupts (IF.03 truncation/version-skew) | CLI bundle emitted from wrong spec version; silent downstream drift | IF.03 async http-json with idempotency=required + content-addressed spec_id (interface_specs.IF.03) — but version-skew possible if FR.05 emitter caches stale DE.05 across retries | Method | IF.03 | 3 | 1 | 3 | MEDIUM LOW | [interface_contract:IF.03] interface_specs.IF.03 ships idempotency=required + retry max_attempts=3 + content-addressed spec_id check (NFR.03); [nfr:NFR.03] Content-addressed spec_id invariant | 3 | 1 | 3 | MEDIUM LOW | committed | 3
FM.04 | surviving from FM.04 ¦ forms: FR.06(primary) | Adapter exceeds non-invasive overhead budget on customer system | Customer system degraded — UC11 non-invasiveness hard-constraint breach | Customer-System Adapter (FR.06) self-meter stale or disabled; polling loop crosses MAX_CUSTOMER_SYSTEM_OVERHEAD_PCT=2% | Method |  | 4 | 2 | 8 | MEDIUM | [form:FR.06] Self-meter against NFR.04 budget; refuse to start if > 2%; [nfr:NFR.04] MAX_CUSTOMER_SYSTEM_OVERHEAD_PCT=2 hard cap | 4 | 2 | 8 | MEDIUM | partial | 2 | Sampled-vs-full-fidelity ingest tradeoff (fmea_early.FM.04.M2) NOT yet committed — customer overhead under burst load still possible.
FM.05 | surviving from FM.05 ¦ forms: FR.07(primary) | Metric stream gap undetected (silent loss) | F.6 Recommendation Engine (FR.08) issues recommendations on stale data; silent wrong-answer mode | OBSERVABILITY TOOLS outage; FR.07 Metric Ingest Service heartbeat emitter degraded | Method |  | 3 | 3 | 9 | MEDIUM HIGH | [form:FR.07] Heartbeat + gap-marker pipeline (NFR.05) over DE.08; [nfr:NFR.05] Stream-gap detection invariant; [form:FR.08] Recommendation Engine refuses to recommend on stale window per fmea_early FM.05.M1 | 3 | 3 | 9 | MEDIUM HIGH | committed | 3
FM.06 | surviving from FM.06 ¦ forms: FR.08(primary) ¦ DN=DN.03/A@AV.01 | Recommendation cadence exceeds RECOMMENDATION_CADENCE_MIN (60 min, est.) | Feedback loop latency budget breached — Module 4 open question realized as incident | F.6 → F.7 in-process IF.10 backpressure absent; LangGraph (DN.03-A) state-machine queue saturation under burst | Method |  | 3 | 2 | 6 | MEDIUM | [form:FR.08] Bounded-queue + shed-load policy (FM.06.M1) | 3 | 2 | 6 | MEDIUM | committed | 2 | RECOMMENDATION_CADENCE_MIN not yet promoted to NFR (FM.06.M2 deferred) — no contract-level enforcement.
FM.07 | surviving from FM.07 ¦ forms: FR.09(primary) ¦ DN=DN.02/A@AV.01 | Traceback emits recommendation without complete citation chain | Auditability criterion fails; downstream NFR-resynth cannot validate rationale | DE.09 catalog miss in pgvector (DN.02-A); FR.09 Traceback Service falls back to LLM completion without KB anchor | Method |  | 3 | 2 | 6 | MEDIUM | [form:FR.09] Fail-closed: Traceback Service refuses to emit DE.10 without all citations resolved (FM.07.M1) | 3 | 2 | 6 | MEDIUM | committed | 2
FM.08 | surviving from FM.08 ¦ forms: FR.01(primary) | Session token replay across projects | Cross-tenant authorization escalation — severe compliance event | Token scope not bound to project_id in FR.01 Auth Service | Method |  | 4 | 1 | 4 | MEDIUM LOW | [form:FR.01] Auth Service binds DE.12 claims to project_id; enforces at every F.N entry via CC.R01 (FM.08.M1); [audit_cross_cut:CC.R01] Per-request authz check against project_id binding | 4 | 1 | 4 | MEDIUM LOW | committed | 4
FM.09 | surviving from FM.09 ¦ forms: FR.05(primary) | CLI bundle (DE.06) ships with secrets embedded | Secret leakage in committed spec artifacts (DE.15) / downstream IDE consumers | FR.05 CLI Bundle Emitter redaction pass regression; credentials_ref interpolation slips raw secret into DE.15 | Method | IF.05 | 4 | 1 | 4 | MEDIUM LOW | [form:FR.05] Redaction pass at F.4 exit; deny-list secret patterns (FM.09.M1); [interface_contract:IF.05] DE.07 payload schema constrains credentials_ref to handles only (FM.09.M2) | 4 | 1 | 4 | MEDIUM LOW | committed | 3
FM.10 | surviving from FM.10 ¦ forms: FR.10(audit-cross-cut) | Audit event not emitted for state-mutating F.N | Audit gap; EC18 retention promise not satisfied | Audit Event Store (FR.10) cross-cut wrapping not applied to a new F.N added after schema lock | Method |  | 3 | 1 | 3 | MEDIUM LOW | [form:FR.10] Audit Event Store wraps F.2/F.3/F.4/F.5/F.6 state mutations (form_function_map.FR.10.realizes_functions); [audit_cross_cut:CC.R02] Lint rule on ffbd.v1 — every state-mutating F.N must carry CC.R02 in source_cc | 3 | 1 | 3 | MEDIUM LOW | committed | 3
FM.11 | surviving from FM.11 ¦ forms: FR.02(primary); FR.09(secondary) | Recommendation loop (DE.10 → F.2) creates specification drift | Specs mutate silently under founders; loses trust + auditability | FR.02 incorporates DE.10 from FR.09 without version-tagging the resulting spec change | Method | IF.09 | 3 | 2 | 6 | MEDIUM | [interface_contract:IF.09] Every recommendation-triggered spec edit bumps version + links DE.10 id in lineage (FM.11.M1) | 3 | 2 | 6 | MEDIUM | committed | 2
FM.12 | surviving from FM.12 ¦ forms: FR.02(primary); FR.03(fallback) ¦ DN=DN.01/A@AV.01 | LLM provider outage (DE.13 unavailable) halts spec generation | System unavailability during outage window — availability criterion breach | Anthropic Claude Sonnet 4.5 (DN.01-A primary) outage; FR.03 fallback LLM provider not warm | Method |  | 2 | 2 | 4 | MEDIUM LOW | [form:FR.03] Spec Generator (Fallback LLM) — circuit-breaker fallback when primary DE.13 unavailable. redundancy_source_fm=FM.12 per form_function_map. | 2 | 2 | 4 | MEDIUM LOW | committed | 1 | FM.12 mitigation crossed redundancy-keyword threshold in T5; FR.03 was added explicitly to discharge it (form_function_map decision_audit DA.02).
FM.13 | NEW (chosen-arch only) ¦ forms: FR.02(primary); FR.03(fallback) ¦ DN=DN.01/A@AV.01 | Primary/fallback LLM split-brain: divergent specs on transient primary degradation | Founder review (FR.04) presented inconsistent spec history; loss of determinism for traceback (FR.09) lineage | Primary Claude Sonnet 4.5 (FR.02) returns degraded but non-error responses near circuit-breaker threshold; some requests hit fallback (FR.03), others primary, producing two valid-but-divergent draft specs for the same DE.01 founder prompt | Method |  | 3 | 2 | 6 | MEDIUM | (none) | 3 | 2 | 6 | MEDIUM | deferred | 4 | No request-level provider stickiness; circuit-breaker (interface_specs IF.01..IF.10 error_rate_threshold_pct=25) trips at session granularity but does not pin a single founder session to one provider. Recommended next-cycle ADR: pin (founder_id, project_id) → provider for session lifetime.
FM.14 | NEW (chosen-arch only) ¦ forms: FR.07(primary); FR.08(secondary) ¦ DN=DN.03/A@AV.01 | Event-bus cascade failure: IF.06 streaming backlog starves IF.10 feedback loop | Recommendation feedback loop stalls; FM.06 cadence breach amplified beyond shed-load capacity | LangGraph (DN.03-A) state-machine consumes IF.06 event-bus and IF.10 in-process stream from same async runtime; IF.06 backlog under burst saturates the runtime, blocking IF.10 message dispatch from FR.09 → FR.08 | Method | IF.06 | 3 | 2 | 6 | MEDIUM | (none) | 3 | 2 | 6 | MEDIUM | none | 3 | No isolation between IF.06 and IF.10 runtimes in chosen LangGraph topology. ADR candidate: separate consumer pool for streaming vs in-process interfaces, or migrate IF.06 to dedicated worker process.
FM.15 | NEW (chosen-arch only) ¦ forms: FR.09(primary) ¦ DN=DN.02/A@AV.01 | pgvector index drift: HNSW recall degrades silently after corpus growth | FR.09 Traceback Service silently misses citation matches; FM.07 fail-closed kicks in at higher rate, blocking emit (DE.10) for valid recommendations | DN.02-A pgvector (Supabase Postgres) HNSW index parameters (m, ef_construction) tuned for initial corpus size; as DE.09 catalog grows past T3 baseline (3289 chunks), recall drops without rebuild. T3 wave-1 noted HNSW as a deferred carry-over. | Method |  | 3 | 3 | 9 | MEDIUM HIGH | [form:FR.09] FM.07 fail-closed surfaces missed citations as emit refusals — partial detectability via secondary symptom | 3 | 3 | 9 | MEDIUM HIGH | deferred | 4 | No periodic recall benchmark scheduled. ADR candidate: add weekly recall@k probe over canonical query set; trigger HNSW rebuild when recall drops below 0.9.
FM.16 | NEW (chosen-arch only) ¦ forms: FR.06(primary) ¦ DN=DN.04/A@AV.01 | Vercel cold-start tax violates IF.06 streaming SLA on FR.06 adapter | Customer metric stream (DE.08) loses leading edge; FR.07 ingest gap-marker fires false-positive, NFR.05 invariant tripped | DN.04-A Vercel serverless cold-starts on FR.06 Customer-System Adapter exceed IF.06 p95_latency_ms=800 SLA after idle window; first metric burst after wake-up dropped or batched | Method |  | 2 | 3 | 6 | MEDIUM | [interface_contract:IF.06] interface_specs IF.06 timeout_ms=1600 + retry max_attempts=3 absorbs first cold-start | 2 | 3 | 6 | MEDIUM | partial | 2 | Vercel free/pro tier cold-start latency is non-contractual. ADR candidate: warm FR.06 via scheduled ping or migrate FR.06 to long-running Cloud Run (matches identity-api pattern in monorepo recommendation).

## Rating Scales
Severity Scale (1-4)
Rating | Label | Conditions
1 | Negligible | Only internal telemetry affected; no founder-visible symptom Cost to remediate < 5% of sprint budget Requires less than 1 day to address Performance adversely affected by less than 5% No compliance, security, or data-loss implication
2 | Marginal | Transient UX degradation that self-heals without founder action Cost 5-10% of sprint budget Requires 1-6 days to address Performance adversely affected by 5-10% No compliance violation, no data loss
3 | Critical | Founder blocked on a core flow (intake / spec review / CLI emit) but no data loss Cost 10-20% of sprint budget Requires 1-2 weeks to address Performance adversely affected by 10-20% SLA breach or near-miss compliance event (recoverable audit gap, no external breach)
4 | Catastrophic | Violation of any hard constraint: EC10 citation floor, UC11 non-invasiveness, MAX_CUSTOMER_SYSTEM_OVERHEAD_PCT=2%, or EC18 retention Compliance breach under SOC2 / HIPAA / GDPR / PCI-DSS Silent data loss, silent wrong-answer, or silent customer-system write Cost > 20% of sprint budget Requires more than 2 weeks to address Performance adversely affected by > 20%
Likelihood Scale (1-5)
Rating | Label | Conditions
1 | Remote | Occurs less than once per quarter under normal operation
2 | Unlikely | Occurs between once per fortnight and once per quarter
3 | Possible | Occurs up to once per week in production
4 | Likely | Occurs more than once per week Or in 5-10% of founder sessions
5 | Frequent | Occurs multiple times per day Or in more than 10% of founder sessions
Criticality Ranges (RPN)
RPN Range | Category | Color
15-20 | HIGH | Red
9-14 | MEDIUM HIGH | Orange
5-8 | MEDIUM | Yellow
3-4 | MEDIUM LOW | Light Green
1-2 | LOW | Green

## Stoplight Before
Residual risk distribution after chosen architecture commits.
| S=1 Negligible | S=2 Marginal | S=3 Critical | S=4 Catastrophic
L5 | 0 | 0 | 0 | 0
L4 | 0 | 0 | 0 | 0
L3 | 0 | 1 | 2 | 0
L2 | 0 | 1 | 5 | 2
L1 | 0 | 0 | 2 | 3
Criticality totals
HIGH | 15-20 | 0
MEDIUM HIGH | 9-14 | 2
MEDIUM | 5-8 | 8
MEDIUM LOW | 3-4 | 6
LOW | 1-2 | 0

## Stoplight After
Residual risk distribution after chosen architecture commits.
| S=1 Negligible | S=2 Marginal | S=3 Critical | S=4 Catastrophic
L5 | 0 | 0 | 0 | 0
L4 | 0 | 0 | 0 | 0
L3 | 0 | 1 | 2 | 0
L2 | 0 | 1 | 5 | 2
L1 | 0 | 0 | 2 | 3
Criticality totals
HIGH | 15-20 | 0
MEDIUM HIGH | 9-14 | 2
MEDIUM | 5-8 | 8
MEDIUM LOW | 3-4 | 6
LOW | 1-2 | 0